MERCHANT CO-PILOT

PROJECT WORK DIVISION & TIME ESTIMATION

An Explainable E-Commerce Intelligence Layer for Revenue-Leak Detection and Actionable Decision Support

| Team Member | Primary Module Ownership |
| --- | --- |
| Anushka | Modules 1, 2, 3, 4, 11, 12 |
| Riya | Modules 5, 6, 7, 8, 9, 10 |

1. Work Division Objective

The 12 final modules are divided equally: 6 modules for Anushka and 6 modules for Riya.

Both partners contribute across Frontend, Backend, and ML/Data development.

Each module has one primary owner responsible for implementation, testing, documentation, debugging, and demonstration.

The estimated schedule is intended as a practical planning baseline and can be adjusted during integration.

2. Module-Wise Ownership and Time Estimation

| No. | Module | Owner | Frontend | Backend | ML/Data / Analytics |
| --- | --- | --- | --- | --- | --- |
| 1 | Merchant & Store Management | Anushka | Login/Register, store UI, profile, settings | Auth APIs, users, stores, roles | Store-level model association |
| 2 | E-Commerce Data Integration | Anushka | Connect-store & sync status | Shopify/WooCommerce adapters, OAuth/API, webhooks | Common data format |
| 3 | Data Processing & Feature Engineering | Anushka | Data quality/status | Cleaning, validation, transformation | RTO, RFM, marketing features, scaling |
| 4 | COD/RTO Prediction | Anushka | RTO risk dashboard | Prediction API, model service integration | Logistic Regression, SGD, evaluation |
| 5 | Customer Churn Prediction | Riya | Churn dashboard | Churn API, prediction storage | RFM, Logistic Regression, SGD |
| 6 | Marketing Spend Efficiency | Riya | Marketing dashboard | Campaign/UTM/cohort APIs | CAC, LTV, channel/cohort analysis |
| 7 | Explainability Engine | Riya | Reason/explanation UI | Explanation API, feature mapping | Feature contributions & ranking |
| 8 | ₹ Impact Estimation | Riya | Impact cards & ranges | Impact calculation API | RTO/churn financial impact |
| 9 | Recommendation / Decision Engine | Riya | Recommendation cards | Rule engine & recommendation API | Prediction/context/confidence → action |
| 10 | Incremental Learning | Riya | Learning status/version UI | Training trigger & model versions | Incremental SGD, labels, drift |
| 11 | Collective Learning / Simulated FedAvg | Anushka | Model status/version | Aggregation & version management | Parameter averaging, warm start |
| 12 | Privacy & Security | Anushka | Security/access UI | RBAC, tenant isolation, tokens, audit, API security | Model/privacy boundary controls |

3. Estimated Time Plan — Anushka

| Module | Main Work | Estimated Time | Suggested Sequence |
| --- | --- | --- | --- |
| 1. Merchant & Store Management | Auth, store management, roles, UI/API | 5–6 days | Week 1 |
| 2. E-Commerce Data Integration | Shopify/WooCommerce, sync, webhooks | 7–8 days | Weeks 2–3 |
| 3. Data Processing & Feature Engineering | Cleaning, validation, features, ML datasets | 7–8 days | Weeks 3–4 |
| 4. COD/RTO Prediction | Training, API, evaluation, dashboard | 8–10 days | Weeks 5–6 |
| 11. Collective Learning / Simulated FedAvg | Aggregation, model versions, warm start | 7–8 days | Weeks 7–8 |
| 12. Privacy & Security | RBAC, tenant isolation, token/webhook security, audit | 7–8 days | Weeks 9–10 |

Estimated implementation effort for Anushka: approximately 41–48 working days.

4. Estimated Time Plan — Riya

| Module | Main Work | Estimated Time | Suggested Sequence |
| --- | --- | --- | --- |
| 5. Customer Churn Prediction | Training, API, evaluation, dashboard | 7–8 days | Weeks 1–2 |
| 6. Marketing Spend Efficiency | UTM, campaign/cohort analysis, dashboard | 6–7 days | Weeks 2–3 |
| 7. Explainability Engine | Feature contributions, API, UI | 5–6 days | Week 4 |
| 8. ₹ Impact Estimation | Financial calculations, API, UI | 4–5 days | Week 5 |
| 9. Recommendation / Decision Engine | Rules, API, recommendation UI | 6–7 days | Weeks 6–7 |
| 10. Incremental Learning | Labels, SGD updates, versions, monitoring | 8–10 days | Weeks 8–10 |

Estimated implementation effort for Riya: approximately 36–43 working days.

5. Overall Project Timeline

Weeks 1–2: Authentication/store foundation, platform integration, churn foundation.

Weeks 3–4: Data processing and feature engineering, marketing analytics, churn implementation.

Weeks 5–6: COD/RTO prediction, explainability, ₹ impact and dashboard integration.

Weeks 7–8: Collective learning, recommendation engine and model-version workflows.

Weeks 9–10: Privacy & Security, incremental learning, complete API integration and system stabilization.

Final 1–2 weeks: End-to-end testing, bug fixing, documentation, deployment preparation, presentation and viva preparation.

6. Frontend / Backend / ML Responsibility Balance

| Area | Anushka | Riya |
| --- | --- | --- |
| Frontend | Auth/store, integrations, data status, RTO, FedAvg, security | Churn, marketing, explainability, impact, recommendations, learning |
| Backend | Auth/store, integrations, processing, RTO, FedAvg, security | Churn, marketing, explainability, impact, recommendations, incremental learning |
| ML/Data | Feature engineering, RTO, FedAvg, privacy controls | Churn, marketing analytics, explainability, impact analytics, incremental learning |

7. Integration and Shared Responsibilities

Both partners will use the common architecture: Next.js frontend, NestJS backend, PostgreSQL/Prisma database, and Python/FastAPI ML service.

Both partners will write unit and integration tests for their own modules.

API contracts, database interfaces, and ML input/output schemas will be agreed jointly before integration.

Both partners will participate in end-to-end testing, final integration, documentation, deployment preparation, presentation, and viva.

Module ownership remains with the assigned partner even when another partner provides integration support.

8. Final Ownership Statement

Anushka — Modules 1, 2, 3, 4, 11, 12    |    Riya — Modules 5, 6, 7, 8, 9, 10

6 modules each • Frontend + Backend + ML/Data contribution by both partners